## Slide 1
Public Works
Capital Improvement Program
3rd Quarter (3Q) Project Updates
January 9, 2024

## Slide 2
The City of Gardena Public Works Department is currently managing
43 projects in Pre-Design to Post Construction (3 > Previous 2Q). $57M in CIP Projects
Across sewers, storm drains, streets, sidewalks, city facilities and parks
($6M > Previous 2Q).
Three (3) additional projects commenced since 2Q
Storm Drain Master Plan
Intelligent Transportation System (ITS) Master Plan
Normandie Railroad Crossing Rehabilitation

## Slide 3
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Planning & Design (Page 1 of 2)
The Public Works Department manages variety of projects in coordination with City Interdepartmental, MTA, Caltrans, UPRR, County, & Other Cities
# | Street/Traffic | Status
1 | Gardena Decorative Street Lighting | 50%
2 | Citywide Wayfinding Entry Signs | 65%
3 | Artesia Blvd Improvements, Ph 2 (Western to Vermont) | 100%
4 | RBB Improvement (Crenshaw to Vermont) | 65%
5 | Rosecrans Ave Regional Traffic Signal Synchronization Project (TSSP) | 60%
6 | RBB Regional TSSP (at Crenshaw) | 100%
7 | MBB Regional TSSP | 100%
8 | Vermont Ave Traffic Signal Upgrade at RBB and Rosecrans | 100%
9 | Development of Intelligent Transportation Study (ITS) Master Plan | 30%
10 | Local Street Improvements FY 2023-2024 | Preliminary
11 | Pedestrian Safety Improvements FY 2023-2024 | Preliminary
12 | Western Avenue RR Crossing Rehabilitation | Planning
13 | Normandie Avenue RR Crossing Rehbilitation | Planning
14 | Vermont Ave Street Improvements (Rosecrans to 135th) | 100%
15 | Intelligent Transportation System (ITS) Master Plan | 30%

## Slide 4
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Planning & Design (Page 2 of 2)
The Public Works Department manages variety of projects in coordination with City Recreation, Metro, Caltrans, UPRR, County, & Other Cities
25 Total CIP Projects in Planning & Design
# | Parks & Facilities | Status
1 | Rosecrans Community Center - Demo Phase | 100%
2 | Rowely Park Gym HVAC Upgrade | 90%
3 | Rowely Park Electronic Signage | 90%
4 | Rowley Park Basketball Court Rehab | 95%
5 | Mas Fukai Park Improvement | 60%
6 | Civic Center Lighting and NCC Electrical Improvements | 35%
7 | Multi-Park Improvements/Master Plan Study (Led by Recs & Human Srvs) | 50%
# | Storm Drain & Sewer System | Status
1 | Storm Drain Master Plan | Preliminary
2 | Sewer Master Plan | Completed
3 | Storm Drain Debris Screen FY 2023-2024 | 0%

## Slide 5
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Construction or Out to Bid
The Public Works Department oversees various types of City projects.
Note: Detail status of all projects are provided on a separate document.
# | Projects | Status
1 | Pedestrian Safety Improvements FY 2022-2023 | Completed
2 | Artesia Blvd Improvements (Ph 1) - Traffic Detour & UPRR Rehab | Completed
3 | Vermont Street Improvement (Artesia to Gardena) | Completed
4 | Budlong (El Segundo to RBB) & Halldale (135th to El Segundo) Improvements | Completed
5 | Local Street Improvement FY 2020-2021 | Completed
6 | Local Street Improvement FY 2021-2022 | 
7 | Local Street Improvement FY 2022-2023 | 
8 | New Marked Crosswalk with PHB on Vermont/133 St | Construction
9 | Fire Station #158 Water Damage Repairs | Completed
10 | Gardena Aquatic & Senior Center - Underground Utility Phase | Construction
11 | Van Ness Avenue Street Improvement (RBB to Marine) | Completed
12 | Gardena Aquatic & Senior Center | Contract Award
13 | Nakaoka Community Center HVAC Upgrade | Construction
14 | Council Chambers AV Upgrade Design/Build | Construction
15 | Sewer Smoke Test on New Hampshire Avenue s/o 170th Street | Completed
16 | EV Charge Ready Installation | Design/Build
17 | Storm Drain Debris Screen FY 2021-2022 | Contract Award
18 | Storm Drain Debris Screen FY 2022-2023 | 

## Slide 6
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 1 of 4)
Local Street Improvements FY 2020-2023
March 2023 – Complete Construction Document
May 2023 – Award $2.4M Construction Contract
July 2023 – Construction Notice to Proceed
December 2023 – Construction Substantially Completed
Construction Scope –
268,000 SF Grind & Overlay Pavement Rehab
520,000 SF Slurry Seal Pavement Rehab
3,300 LF Curb & Gutter Reconstruction
7,300 SF Cross Gutters
5,600 SF Sidewalk Reconstruction
28 Access Ramp Improvements
820 SF Alley and Driveway Improvements
Additional scope; adjust utility valves & MHs,
traffic striping & signings, traffic loops,
replant trees, etc.

## Slide 7
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 2 of 4)
Local Street Improvements FY 2020-2023 at Various Locations
Completed Streets –
Ardath Ave (129th to 134th)
129th Pl (Cul-de-sac to Ardath)
132nd Pl (Cul-de-sac to Ardath)
135th Pl (Cul-de-sac to Ardath)
141st St (Cul-de-sac to Ardath)
139th St (Ardath to Van Ness)
Gramercy Pl (Marine to 154th)
St Andrews Pl (Marine to 154th)
152nd St (Gramercy to Western)
153rd St (Gramercy to Western)
154th St (Gramercy to Western)
162nd St (Western to Normandie)
Gardena Blvd (Western to Normandie)
168th St (Halldale to Cul-de-sac)
169th St (La Salle to Denker)
170th St (Denker to Normandie/Railroad)
169th St (Brighton to Brighton)
E San Luis St (Brighton Ave to Bright Way)
Denker Ave (169th to 170th)
Halldale Ave (169th to 170th)
Brighton Ave (Railroad to 170th)
Berendo Ave (170th to Willows)
S Catalina Ave (170th to Willows)
180th St (Western to Denker)
179th St (Evelyn to Normandie)
Evelyn Ave (178th to 182nd)
Total Length = 25,1212 LF (4.76 Miles)

## Slide 8
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 3 of 4)
Local Street Improvements FY 2020-2023

## Slide 9
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 4 of 4)
Local Street Improvements FY 2020-2023

## Slide 10
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 2 (Page 1 of 3)
Van Ness Street Improvements (Marine to RBB)
March 2023 – Complete Construction Document
August 2023 – Award $1.4M Construction Contract
October 2023 – Construction Notice to Proceed
December 2023 – Construction Substantially Completed
Construction Scope –
155,000 SF Grind & Overlay Pavement Rehab
300 LF Curb & Gutter Reconstruction
3,400 SF Sidewalk Reconstruction
10 Reconstruct Access Ramps
1,000 SF driveway and alley approach
Ped Push Button with Touchless Accessible
Additional scope; battery backup traffic signal,
Ped Push Button w/ Touchless Accessible,
replanting trees, traffic striping & signings,
traffic loops, etc.

## Slide 11
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 2 (Page 2 of 3)
Van Ness Street Improvements (Marine to RBB)
Notes: Ped push button and battery back up installation remaining.

## Slide 12
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 2 (Page 3 of 3)
Van Ness Street Improvements (Marine to RBB)
Notes: Ped push button and battery back up installation remaining.

## Slide 13
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 3 (Page 1 of 3)
City Council Chamber Audio Visual (A/V) Upgrade
September 2023 – Award $81,888 Design Build Contract
October 2023 – Notice to Proceed in design and material procurement
December 2023 – Construction Start (4 Weeks)
Construction Scope –
(4) 30x optical zoom 4K video cameras & (1) camera controller/switcher
Webpresenter that will connect to laptop or PC web conferencing
43” Multiview monitor in the broadcast control room
Dual 7” rack mounted monitors in the broadcast room
Ethernet switch for the AV system lives
4K HDMI broadcast system for streaming and recording
(1) 24” podium & (12) desktop goosenect microphones
(2) digital signal processors to handle all audio routing, echo
cancellation, and audio processing and controllers
(8) 6.5” ceiling mounted speakers & (2) 4 channel 60W sound
amplifiers & (2) clock audio capacitive touch switches
(5) desktop speakers at the council members’ dais
All other incidental materials and installation to provide
audio and video digital broadcasting and re-broadcasting
in 4k high definition.

## Slide 14
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 3 (Page 2 of 3)
City Council Chamber A/V Upgrade – Construction Images
Notes: Ped push button and battery back up installation remaining.

## Slide 15
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 3 (Page 3 of 3)
City Council Chamber A/V Upgrade – Construction Images

## Slide 16
3Q CIP Summary Recap:
25 Projects in Design or Planning (= 2Q)
18 Projects in Construction or Out to Bid (3 > 2Q)
43 Projects in total (3 > 2Q)
8 Completed Projects (4 > 2Q)
$57M in Total CIP Budget ($6M > 2Q)
Gardena Aquatic & Senior Center Project –
December 12, 2023, Additional $6.2M
General Fund Reserve Amended by
the City Council

## Slide 17
PUBLIC WORKS CIP – 3Q PROJECT UPDATES
QUESTIONS?