## Slide 1
Public Works
Capital Improvement Program
2nd Quarter (2Q) Project Updates
October 10, 2023

## Slide 2
The City of Gardena Public Works Department is currently managing
40 projects in Pre-Design to Post Construction. $51M in Capital Improvement Projects across sewers, storm drains, streets, sidewalks, city facilities and parks.
Three (3) additional projects amended
since Q1, in the total amount of $350,777:
Council Chamber AV Upgrade ($81,888)
EV Charge Ready ($268,885)
Western Avenue UPRR Improvement ($TBD)

## Slide 3
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Planning & Design (Page 1 of 2)
The Public Works Department manages variety of projects in coordination with City Interdepartmental, MTA, Caltrans, UPRR, County, & Other Cities
# | Street/Traffic | Status
1 | Gardena Decorative Street Lighting | 30%
2 | Citywide Wayfinding Entry Signs | 65%
3 | Artesia Blvd Improvements, Ph 2 (Western to Vermont) | 100%
4 | RBB Improvement (Crenshaw to Vermont) | 65%
5 | Rosecrans Ave Regional Traffic Signal Synchronization Project (TSSP) | 60%
6 | RBB Regional TSSP (at Crenshaw) | 90%
7 | MBB Regional TSSP | 90%
8 | Vermont Ave Traffic Signal Upgrade at RBB and Rosecrans | 100%
9 | Development of Intelligent Transportation Study (ITS) Master Plan | 30%
10 | Local Street Improvements FY 2023-2024 | Preliminary
11 | Pedestrian Safety Improvements FY 2023-2024 | Preliminary
12 | Western Avenue RR Crossing Rehabilitation | Planning
13 | Vermont Ave Street Improvements (Rosecrans to 135th) | 100%

## Slide 4
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Planning & Design (Page 2 of 2)
The Public Works Department manages variety of projects in coordination with City Recreation, Metro, Caltrans, UPRR, County, & Other Cities
25 Total CIP Projects in Planning & Design
# | Parks & Facilities | Status
1 | Rosecrans Community Center - Demo Phase | 95%
2 | Rowely Gym HVAC Upgrade | 80%
3 | Rowely Park Electronic Signage | 60%
4 | Rowley Park Basketball Court Rehab | 90%
5 | Mas Fukai Park Improvement | 60%
6 | Civic Center Lighting and NCC Electrical Improvements | Preliminary
7 | Multi-Park Improvements/Master Plan Study (Led by Recs & Human Srvs) | 35%
# | Storm Drain & Sewer System | Status
1 | Storm Drain Debris Screen FY 2021-2022 | 100%
2 | Storm Drain Debris Screen FY 2022-2023 | 
3 | Sewer Master Plan | Completed
4 | Storm Drain Master Plan | 0%
5 | Storm Drain Debris Screen FY 2023-2024 | 0%

## Slide 5
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Construction or Out to Bid
The Public Works Department oversees various types of City projects.
Note: Detail status of all projects are provided on a separate document.
# | Projects | Status
1 | Pedestrian Safety Improvements FY 2022-2023 | Construction
2 | Artesia Blvd Improvements (Ph 1) - Traffic Detour & UPRR Rehab | Complete
3 | Vermont Street Improvement (Artesia to Gardena) | Complete
4 | Budlong (El Segundo to RBB) & Halldale (135th to El Segundo) Improvements | Complete
5 | Local Street Improvement FY 2020-2021 | Construction
6 | Local Street Improvement FY 2021-2022 | 
7 | Local Street Improvement FY 2022-2023 | 
8 | New Marked Crosswalk with PHB on Vermont/133 St | Construction
9 | Fire Station #158 Water Damage Repairs | Complete
10 | Gardena Aquatic & Senior Center - Underground Utility Phase | Construction
11 | Van Ness Avenue Street Improvement (RBB to Marine) | Contract Award
12 | Gardena Aquatic & Senior Center | To Rebid
13 | Nakaoka Community Center HVAC Upgrade | Out to Bid
14 | Council Chambers AV Upgrade Design/Build | Contract Award
15 | EV Charge Ready Installation | Contract Award
Notes: In total 40 projects and 3 more than previous quarter.

## Slide 6
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 1 of 4)
Artesia Blvd (Western to Vermont) –
Phase 1, Railroad Crossing Improvement
January 2023 – Award Construction Contract
April 2023 – Finalized Agreement with UPRR
October 2023 – Construction Complete
Phase 2, Street Improvements
June 2023 – LA MTA Award Additional $2.3M,
Measure R Highway Funds ($3.7M Total Budget)
November 2023 – Solicit Bids and Award
Construction Contract
Summer 2024 – Start Construction
Notes: Phase 2 bid soliciting schedule is pending Funding Agreement from LA MTA.

## Slide 7
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 2 of 3)
Artesia Blvd – Phase 1, Railroad Crossing Improvement (Before Images)
Artesia Blvd/RR – South View
Artesia/Normandie/RR – Southeast View

## Slide 8
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 2 of 3)
Artesia Blvd – Phase 1, Railroad Crossing Improvement (Construction Images)

## Slide 9
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1 (Page 3 of 3)
Artesia Blvd – Phase 1, Railroad Crossing Improvement (After Images)
Artesia Blvd/RR – South View
Artesia/Normandie/RR – Southeast View

## Slide 10
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 2 (Page 1 of 3)
Fire Station #158 – Water Damaged Ceiling Rehab
October 2022 – Construction Contract Award
January 2023 – Construction Notice to Proceed
August 2023 – Filed Notice of Completion
Construction Scope –
7,700 SF new ceiling grid system and tiles
New LED lighting fixtures and controls
New HVAC registers and exhaust fans
New HVAC insulation
Asbestos and lead abatement
Drainage pipe repairs
Shower floors
Painting

## Slide 11
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 2 (Page 2 of 3)
F.S. #158 – Water Damaged Ceiling Rehab (Before Images)

## Slide 12
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 2 (Page 3 of 3)
Fire Station #158 – Water Damaged Ceiling Rehab (After Images)

## Slide 13
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 3 (Page 1 of 2)
Vermont Street Improvements (Artesia to Gardena Blvd)
March 2023 – Complete Construction Document
April 2023 – Award $791K Construction Contract
July 2023 – Construction Notice to Proceed
September 2023 – Construction Substantially Completed
Construction Scope –
102,000 SF Grind & Overlay Pavement Rehab
125 LF Curb & Gutter Reconstruction
770 SF Sidewalk Reconstruction
2 Reconstruct Access Ramps
7 Ped Push Button with Touchless Accessible
Additional scope; cross gutter, adjust utility valves &
MHs, traffic striping & signings, traffic loops,
traffic signal battery backup, etc.

## Slide 14
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 3 (Page 2 of 2)
Vermont Street Improvements (Artesia to Gardena Blvd)
Notes: Ped push button and battery back up installation remaining.

## Slide 15
CIP Summary Recap:
25 Projects in Design or Planning
15 Projects in Construction or Out to Bid
40 Projects in total, including 3 New Projects in 2Q
$51M in Total CIP Budget, including Additional $350,777 in 2Q
Additional Funds to be amended:
Artesia Blvd Street Improvements – June 2023, LA Metro Approved $2.3M Measure R Highway
Vermont/Rosecrans/RBB Traffic Signal Improvements – June 2023, LA Metro Approved $728K
Measure R Highway
RBB Street Improvements – September 2023, LA Metro Approved $5.6M Measure M Highway
Mas Fukai Park Improvements - $2M State Budget Allocation (TBD)
Rowley Park Gymnasium Renovation - $3M State Budget Allocation (TBD)
Total $65M Forecasted CIP Budget
Notes: Confirming with SBCCOG on $5.5M award..

## Slide 16
PUBLIC WORKS CIP – 2Q PROJECT UPDATES
QUESTIONS?