## Slide 1
Procurement Practices and Policies
Special Study Session
City of Gardena
City Council
October 24, 2023

## Slide 2
Agenda
City of Gardena Purchasing Policy
Project Contingencies
Increasing City Manager Purchasing Authority
Prepare for City Manager / City Council Approval
2

## Slide 3
City of Gardena Purchasing Policy Rev. 10-26-2017
Establishes methods of procurements
Establishes approval thresholds
Identifies special provisions
Establishes procedures for purchasing City supplies, services and equipment at lowest possible cost comensurate with quality needed
Defines the specific methods used for procurement of goods and services
Outlines the encumbrance authority for the City Council, City Manager and Purchasing Officer
Discusses allowable purchasing methods outside of traditional solicitations or quotes, such as sole source, cooperative procurements, etc.
3

## Slide 4
Current Policy
Approval Authority
Purchases greater than $30,000
City Council
City Manager
Purchases under $30,000
4

## Slide 5
  Goods or services valued under $50,000
  Number of quotes determined by size of complexity of project and market conditions
  May be formal or informal bids
  Fair and reasonable, best value
Procurement Methods
Request for Proposals (RFP)
Invitation for Bids (IFB)
Request for Quote (RFQ)
  Based on scope of work
  Evaluation criteria and scoring (price is only one component)
  Price negotiations
  Commonly used for construction
  Used in formal bids that are estimated to be greater than $50,000
  Adheres to rules for publishing and posting notices, and maintaining a bidders list
Uniform Construction Cost Accounting Procedures
  Develop a list of qualified bidders for categories of work
  Different levels of bidding depending on dollar thresholds
  Up to $175,000 informal bid using CM authority
5

## Slide 6
Procurement Methods
Exceptions to Formal Bidding
Emergency
Sole Source
Cooperative Purchases / Piggybacking
  City Manager authority
  Needed to prevent immediate interruption of necessary City services or safeguard life, property or public health
  No informal/formal bidding required
  Used when no advantage to competitive bidding
  Distinct specifications and requirements
  Determined to be the only reasonably known source for supply
  Leverages economies of scale
  Originally solicited by other government/quasi public or non-profit entities
  For goods or services
6

## Slide 7
Methods of Issuing Bids/Solicitations
PlanetBids
CR Planwell
Informal Quotes/Requests
  eProcurement software for posting solicitations, broad dissemination to registered DBEs, managing registered vendors
  Provides access to similar solicitations made by other public agencies
  Hosts project documents for public bids from the Public Works Department
  Includes all plans, specifications, addendums, and other items
  May be done through email, phone calls, etc.
7

## Slide 8
Steps for Project Execution
Complete Appropriate Procurement
Determine Project Budget
Prepare for City Manager / City Council Approval
  City Attorney review of contract, as required
  Evaluate bids/proposals as required
  Responsiveness determinations (reference checks, suspended/debarred, etc.)
  Notify bidders within protest timeframe
  Evaluate need for project contingency
  Finalize total project cost
  Write staff report
  Obtain appropriate documents and signatures
  Develop presentation, as needed
8

## Slide 9
A future event or circumstance which is possible but cannot be predicted with certainty.
"a detailed contract that attempts to provide for all possible contingencies."
Oxford Dictionary
Project Contingencies
9

## Slide 10
Contingencies
(Range from 10 to 25 percent)
Why are contingencies needed?
When are they used?
How are they used?
  Not all potential scenarios can be included in an accurate scope of work
    Incentive for City to have a good scope of work to guarantee best/most accurate cost from vendor/supplier
    We want to avoid vendor/supplier inflating costs to account for every potential scenario
  Without contingencies, changes would need to be re-procured, jeopardizing project consistency and cost
  Impossible to account for all unforeseen conditions
  City needs related/additional work that was not included in original scope (need more outreach, need to move a piece of equipment, need additional training hours on a technology project)
  Discovery of unforeseen conditions (bad soil conditions, flooding of project site due to rain)
  Council Directives for specific changes
  Prior City approval of change - both for cost and scope
  May use both formal and informal processes to document the change
10

## Slide 11
City Projects
Public Works
Review of 22 Public Works Capital Projects
Use of Contingencies
  Types of projects include: consultant and contractors used for street pavement improvements, building rehabilitations, pedestrian safety improvements, etc.
  Contingency used in 32% of the projects (7 projects)
    These projects ranged in value from $71,900 to $1,481,800.
    Contingency on these projects was average of 6% of project values.
  Of the 22 projects, 68% (15) came in at or under original budget.
  Quantity overruns – Additional asphalt, concrete installation and removal, curb & gutter, sidewalk, etc.
  Additional scope – Requested by residents, businesses and constituents to construct additional access ramps, pavement striping & signs, traffic pedestrian push/audible buttons, etc.
  Unforeseen conditions – Deteriorated water, storm/roof drains and sewer pipes, HVAC insulation, analog to digital conversion, etc.
11

## Slide 12
City Projects
GTrans
Review of 32 GTrans Projects
Use of Contingencies
  Types of projects include: suppliers and contractors used for CNG station construction, new technology deployment, and bus purchase and manufacturing.
  Contingency used in 16% of the projects (5 projects)
    These projects ranged in value from $798,987 to $13,014,913.
    Contingency on these projects was average of 6% of project values.
  Of the 32 projects, 84% (27) have not used contingency to date.
  CNG Station Construction - address poor soil conditions, expand footprint of compound to accommodate emergency generator.
  Deployment of GRID (CAD/AVL and Real Time Info) - additional training, connecting radios to the INSB network.
  Bus Purchases - engineering improvements to components from base contract, increase in steel cost.
12

## Slide 13
Considerations for Increasing City Manager Purchasing Authority
Increased project costs
Need for improved project efficiencies
Consistent with similarly-sized cities
  Cost increases for goods and services over time have resulted in more projects that exceed authority of City Manager.
  Increased complexity of projects and regulations require more project development, and thus additional procurements coming before City Council. Each adds additional time and delay to the project timeline.
  Gardena is below the average purchasing authority threshold for cities of similar sizes across the County.
13

## Slide 14
City Manager Approval
Comparison with Municipal Peers
City of Gardena
$30,000
City of El Segundo
$50,000
City of Montebello
$50,000
City of Pico Rivera
$50,000
City of Signal Hill
$50,000
City of South Gate
$50,000
14

## Slide 15
Next Steps
Develop Draft Policy
Recomendation to City Council
Staff will draft a policy to increase the City Manager approval authority for purchases.
Draft policy recommendation will be brought for Council consideration.
15

## Slide 16
Questions?
16