## Slide 1
Public Works
Capital Improvement Program (CIP) Project Updates
July 11, 2023

## Slide 2
The City of Gardena Public Works Department currently has 37 projects as of July 2023 in Pre-Design to Post Construction. Public Works currently has $51 M in Capital Improvement Projects across sewers, storm drains, streets, sidewalks, city facilities and parks.

## Slide 3
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Planning & Design (Page 1 of 2)
The Public Works Department manages variety of projects in coordination with City Interdepartmental, MTA, Caltrans, UPRR, County, & Other Cities
# | Street/Traffic | Status
1 | Gardena Decorative Street Lighting | Planning
2 | Citywide Wayfinding Entry Signs | 100%
3 | Artesia Blvd Improvements, Ph 2 (Western to Vermont) | 95%
4 | Vermont Street Improvement (Rosecrans to 135th) | 100%
5 | RBB Improvement (Crenshaw to Vermont) | Preliminary
6 | Van Ness Ave Street Improvement (RBB to Marine) | 100%
7 | Rosecrans Ave Regional Traffic Signal Synchronization Project (TSSP) | Preliminary
8 | RBB Regional TSSP (at Crenshaw) | Preliminary
9 | MBB Regional TSSP | Preliminary
10 | Vermont Ave Traffic Signal Upgrade at RBB and Rosecrans | 100%
11 | Development of Intelligent Transportation Study (ITS) Master Plan | Preliminary
12 | Annual Local Street Improvements FY 2023-2024 | 0%
13 | Annual Pedestrian Safety Improvements FY 2023-2024 | 0%

## Slide 4
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Planning & Design (Page 2 of 2)
The Public Works Department manages variety of projects in coordination with City Recreation, Metro, Caltrans, UPRR, County, & Other Cities
# | Parks & Facilities | Status
1 | Rosecrans Community Center - Demo Phase | 90%
2 | Rowley Park Gymnasium HVAC Upgrade | Preliminary
3 | Rowley Park Electronic Signage | 70%
4 | Rowley Park Basketball Court Rehab | 50%
5 | Mas Fukai Park Improvement | 30%
6 | Gardena Aquatic & Senior Center | 95%
7 | Nakaoka Community Center HVAC Upgrade | 80%
8 | Civic Center Lighting Improvement | Preliminary
9 | Multi-Park Improvements/Master Plan Study (Led by Recs & Human Services) | Preliminary
# | Storm Drain & Sewer System | Status
1 | Storm Drain Debris Screen FY 2021-2022 | 95%
2 | Storm Drain Debris Screen FY 2022-2023 | 
3 | Sewer Master Plan | 100%
4 | Storm Drain Master Plan | 0%
5 | Storm Drain Debris Screen FY 2023-2024 | 0%
27 Total CIP Projects in Planning & Design

## Slide 5
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Current Projects in Construction or Out to Bid
The Public Works Department oversees various types of City projects.
Note: Detail status of all projects are provided on a separate document.
# | Projects | Status
1 | Pedestrian Safety Improvements FY 2022-2023 | Out to Bid
2 | Artesia Blvd Improvements (Ph 1) - Traffic Detour & UPRR Rehab | Contract Awarded
3 | Vermont Street Improvement (Artesia to Gardena) | Contract Awarded
4 | Budlong (El Segundo to RBB) & Halldale (135th to El Segundo) Improvements | 95%
5 | Local Street Improvement FY 2020-2021 | Contract Awarded
6 | Local Street Improvement FY 2021-2022 | 
7 | Local Street Improvement FY 2022-2023 | 
8 | New Marked Crosswalk with PHB on Vermont/133 St | Contract Awarded
9 | Fire Station #158 - Water Damaged Ceiling Repair | 95%
10 | Gardena Aquatic & Senior Center - Underground Utility Phase | 100%

## Slide 6
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 1
Gardena Aquatic and Senior Center
December 2022 – Complete Demolition Phase
May 2023 – Pre-Qualified 3 General Contractors
June 2023 - Underground Utility Construction in Progress
July 2023 – Complete Final Construction Documents
September 2023 - Solicit Bids and Award Construction Contract
Winter 2023 – Start Construction (1 year duration)

## Slide 7
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 2
Mas Fukai Park Improvement
July 2022 – Complete Master Plan Study
December 2022 – Award Design Services Contract
June 2023 - Final Design Development
February 2024 – Complete Final Construction Documents
Summer 2024 – Start Construction

## Slide 8
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 3
Rosecrans Community Center
August 2023 – Complete Demolition Phase Final Construction Documents (CDs)
October 2023 - Solicit Bids and Award Demolition Contract
November 2023 – Start Demolition Construction
Spring 2024 - Conceptual and Program Development (Part of Citywide Park Master Plan Study)
TBD - New Community Center Construction Document Phase

## Slide 9
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 4
Artesia Blvd Street Improvement (Western to Vermont)
January 2023 – Contract Award Traffic Detour & UPRR Crossing Improvement
June 2023 – LA MTA Award Additional $2.3M, Measure R Highway, Funds ($3.7M Current Budget)
July 2023 – Complete Street Improvement Phase Construction Document
September 2023- Solicit Bids and Award Street Improvement Construction Contract
Winter 2023 – Start Construction
Artesia Blvd
Western Ave
Vermont Ave

## Slide 10
  CITY OF GARDENA
  PUBLIC WORKS CIP UPDATE
Highlighted Project 5
Vermont Avenue Traffic Signal Upgrade at RBB & Rosecrans
June 2023 - Metro Granted Additional $728K, Measure R Highway, Funds
July 2023 – Complete Final Construction Document (Pending City of LA Permit Approval)
September 2023 - Solicit Bids and Award Construction Contract
June 2024 – Start Construction (6-8 Months Material Lead Time)

## Slide 11
In additional to 37 CIP Projects
($51M) currently in design/ planning or construction phases as of July 2023, there are additional $13.5M pending approval during the FY 2023-2024.
Artesia Blvd Street Improvements - $2.3M Measure R Highway
Vermont/Rosecrans/RBB Traffic Signal Improvements - $728K
Mas Fukai Park Improvements - $2M State Budget Allocation (TBD)
Rowley Park Gymnasium Renovation - $3M
State Budget Allocation (TBD)
RBB Street Improvements - $5.5M Measure M
Highway (TBD)
Total Potential Budget of $64.5M
Capital Improvement Projects

## Slide 12
PUBLIC WORKS CIP PROJECT UPDATES
QUESTIONS?